## ⚙︎
NAME OF SHEETS:

## Report
PROJECT MANAGEMENT REPORT
PROJECT NAME: | Project Name | PROJECT STATUS: |  | DELAYED
PROJECT SPONSOR: | Name of Project Sponsor
PROJECT MANAGER: | Pedro Penduko |  | STATUS DATE: | 2022-02-12
PROJECT HEALTH
PROJECT TIMELINE
PROGRESS
48%
COMPLETE
SPENT
REMAINING

## Dashboard
[ INSERT LOGO HERE] | PROJECT NAME |  | SUNDAY
| COMPANY NAME | 2022-02-13
48%
OVERALL STATUS
DELAYED
GANTT CHART
REPORT
QUICK LINKS
RISK AND ISSUES
COMMUNICATION PLAN
STAKEHOLDERS
ABOUT THE TEAM
Started:
Expected End Date:
Days Passed:
13-Feb-22
13-Feb-22
0
PROJECT HEALTH
15
RISKS
234
ISSUES
255
ACTION ITEMS
BUDGETING
TIMELINE
TIMELINE SLICERS
TABLE OF ONGOING PHASES

## Work Package
[ Insert Company Logo here] |  | COMPANY NAME
Project Name
| Project Start Date | 2022-02-13 | [13 empty] | Not Started ¦ In Progress | [9 empty] | Complete | [5 empty] | Today
| Project Sponsor | Name of Project Sponsor
| Project Manager | Name of Project Manager | [11 empty] | Display Week | [5 empty] | 1
| Project Champion | Name of Project Champion
[14 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
[14 empty] | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14 | [6 empty] | 2022-03-21 | [6 empty] | 2022-03-28 | [6 empty] | 2022-04-04
 | time axis 2022-02-14 to 2022-04-10
WBS | PHASE | LEAD | PREDECESSOR | PLANNED START | PLANNED DAYS | PLANNED END | ACTUAL START | ACTUAL DAYS | ACTUAL END | WORK DAYS | STATUS | % DONE | WBS_LVL | time axis 2022-02-14 to 2022-04-10
1 | PHASE A |  |  | 2022-02-12 | 5 | 2022-02-17 |  |  |  |  | COMPLETE | 100 | 2
1.1 | SUB-PHASE A1 | [9 empty] | COMPLETE |  | 3
1.2 | SUB-PHASE A2 | [9 empty] | COMPLETE |  | 3
2 | PHASE B | [9 empty] | COMPLETE | 100 | 2
2.1 | SUB-PHASE B1 | [9 empty] | COMPLETE |  | 3
2.2 | SUB-PHASE B2 | [9 empty] | COMPLETE |  | 3
2.2.1 | SUB-PHASE B2a | [9 empty] | OVERDUE |  | 4
2.2.2 | SUB-PHASE B2b | [9 empty] | NOT STARTED |  | 4
3 | PHASE C | [9 empty] | NOT STARTED | 40 | 2
3.1 | SUB-PHASE C1 | [9 empty] | OVERDUE | 40 | 3
3.1.1 | SUB-PHASE C2a | [9 empty] | NOT STARTED | 40 | 4
4 | PHASE D | [9 empty] | IN PROGRESS | 10 | 2
5 | PHASE E | [9 empty] | NOT STARTED | 0 | 2
5.1 | SUB-PHASE E1 | [9 empty] | NOT STARTED | 0 | 3
5.2 | SUB-PHASE E2 | [9 empty] | NOT STARTED | 0 | 3
#VALUE!
#VALUE!
#VALUE!
Formulas:
Display Week = [Display Week, row below]
Insert Phase
Add Sub-Phase
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## Project Data
PROJECT DETAILS |  | WBS | PHASE | MAIN PHASE | SP-1 | SP-2 | SP-3 | SP-4 | LEAD | PREDECESSOR | WBS Level | START | END | DAYS | STATUS | CMPLT | % DONE | WORK DAYS | [16 empty] | PROJECT STATUS | DROPDOWN ITEMS
Project Name | Project Name | 1 | Project Kick-off | Project Kick-off | NONE | NONE | NONE | NONE | AC |  | 2 | 2020-03-25 | 2020-03-29 | 5 | IN PROGRESS |  | 100% | 3 | TASK STATUS TRACKING |  |  | BUDGET |  |  | RISKS & PENDING ACTIONS | [9 empty] | NOT STARTED | REQUIRED COMMUNICATION | R/I IMPACT | RISK/ISSUE STATUS | COMMUNICATION PLAN STATUS | CRITERIA | WBS Level | PHASE | START | END | DAYS SINCE START | RANGE DAYS
Project Sponsor | Juan Dela Cruz | 2 | Data Sanitation and training content creation | Data Sanitation and training content creation | NONE | NONE | NONE | NONE | KT/DT/ BP |  | 2 | 2020-04-13 | 2020-05-12 | 22 | COMPLETE | 1 | 100% | 22 | STATUS | COUNT | PERCENT(%) | PROJECTED | ACTUAL | REMAINDER | TASK | RISKS |  |  | ISSUES |  |  | ACTION ITEMS |  |  | ON TRACK | [5 empty] | 2 | Project Kick-off | 2020-03-25 | 2020-03-29 | 690
Project Manager | Pedro Penduko | 2.1 | Data Extraction | Data Sanitation and training content creation | Data Extraction | NONE | NONE | NONE | Bpublico |  | 3 | 2020-04-13 | 2020-04-17 | 5 | COMPLETE | 1 | 100% | 5 | NOT STARTED | 4 | 9.524% | 5000 | 1000 | 4000 |  | HIGH | MEDIUM | LOW | HIGH | MEDIUM | LOW | PENDING | IN PROGRESS | Closed | AT RISK | Daily Huddle | HIGH | Pending |  |  |  | Data Sanitation and training content creation | 2020-04-13 | 2020-05-12
Project End Date |  | 2.1.1 | Data Clean-up | Data Sanitation and training content creation | Data Extraction | Data Clean-up | NONE | NONE | Ktamis |  | 4 | 2020-04-17 | 2020-05-07 | 21 | COMPLETE | 1 | 100% | 15 | IN PROGRESS | 8 | 19.05% |  | 20% | 80% | TOTAL | 2 | 0 | 0 | 150 | 62 | 22 | 8 | 9 | 238 | DELAYED | Weekly Huddle | MEDIUM | Resolution In Progress |  |  |  | Development | 2020-04-08 | 2020-05-08
Project Start Date | 2022-02-13 | 2.1.2 | Product Update in JDA and My Suki | Data Sanitation and training content creation | Data Extraction | Product Update in JDA and My Suki | NONE | NONE | Ktamis |  | 4 | 2020-04-17 | 2020-04-20 | 4 | COMPLETE | 1 | 100% | 2 | OVERDUE | 10 | 23.81% | [14 empty] | Monthly Huddle | LOW | Closed |  |  |  | System Integration Testing | 2020-05-01 | 2020-05-11
Project End Date | 2022-02-13 | 2.1.3 | Data Clean-up Sign-off | Data Sanitation and training content creation | Data Extraction | Data Clean-up Sign-off | NONE | NONE |  |  | 4 | 2020-05-07 | 2020-05-07 | 1 |  |  | 0% | 1 | COMPLETE | 20 | 47.62% |  |  |  | RISKS & PENDING ACTIONS | [10 empty] | Email | [5 empty] | Training | 2020-05-07 | 2020-05-12
Current Phase |  | 2.1.4 | Training Content Creation - Store Operation | Data Sanitation and training content creation | Data Extraction | Training Content Creation - Store Operation | NONE | NONE | Bpublico |  | 4 | 2020-04-20 | 2020-05-12 | 23 | COMPLETE | 1 | 100% | 17 | TOTAL TASKS | 42 | 100% |  |  |  | TASK | HIGH | MEDIUM | LOW | [7 empty] | Conference Meeting (Office) | [5 empty] | PRG Business Process Creation - BRD | 2020-04-17 | 2020-05-13
TODAY | 2022-02-13 | 2.1.5 | Training Content Creation - For Customer | Data Sanitation and training content creation | Data Extraction | Training Content Creation - For Customer | NONE | NONE | Bpublico |  | 4 | 2020-04-20 | 2020-05-12 | 23 | COMPLETE | 1 | 100% | 17 |  |  | 52.38% | [7 empty] | SUM | [6 empty] | Conference Meeting (Online) | [5 empty] | Configuration and Migration | 2020-05-11 | 2020-05-15
Project Status: | DELAYED | 2.1.6 | Training Content Sign-off | Data Sanitation and training content creation | Data Extraction | Training Content Sign-off | NONE | NONE |  |  | 4 | 2020-05-12 | 2020-05-12 | 1 |  |  | 0% | 1 | [6 empty] | RISKS | 2 | 5 | 8 | 15 | [12 empty] | Data Migration | 2020-05-11 | 2020-05-15
Company Name | COMPANY NAME | 3 | Development | Development | NONE | NONE | NONE | NONE | BP |  | 2 | 2020-04-08 | 2020-05-08 | 23 | COMPLETE | 1 | 100% | 23 | [6 empty] | ISSUES | 150 | 62 | 22 | 234 | [12 empty] | Infrastructure | 2020-04-30 | 2020-05-12
Days Passed | 0 | 3.1 | Suki App | Development | Suki App | NONE | NONE | NONE |  |  | 3 | 2020-04-08 | 2020-04-08 | 1 | COMPLETE | 1 | 100% | 1 | [6 empty] | ACTION ITEMS | 8 | 9 | 238 | 255 | [12 empty] | Pre Live Checklist/Preparation | 2020-05-11 | 2020-05-15
|  | 3.1.1 | Suki Hub | Development | Suki App | Suki Hub | NONE | NONE |  |  | 4 | 2020-04-08 | 2020-04-08 | 1 | COMPLETE | 1 | 100% | 1 | [23 empty] | Dry Run | 2020-05-11 | 2020-05-26
|  | 3.1.2 | Picker-Checker | Development | Suki App | Picker-Checker | NONE | NONE |  |  | 4 | 2020-04-08 | 2020-04-08 | 1 | COMPLETE | 1 | 100% | 1 | [23 empty] | Marketing Advertisements/Promotions | 2020-05-28 | 2020-05-29
|  | 3.1.3 | Barter Middleware (Merging to prod version) | Development | Suki App | Barter Middleware (Merging to prod version) | NONE | NONE |  |  | 4 | 2020-05-01 | 2020-05-08 | 8 | COMPLETE | 1 | 100% | 6 | [23 empty] | Go Live | 2020-05-15 | 2020-12-07
|  | 3.1.4 | POS Interface | Development | Suki App | POS Interface | NONE | NONE |  |  | 4 | 2020-05-01 | 2020-05-08 | 8 | COMPLETE | 1 | 100% | 6
|  | 3.1.5 | Core Middleware | Development | Suki App | Core Middleware | NONE | NONE |  |  | 4 | 2020-05-01 | 2020-05-08 | 8 | COMPLETE | 1 | 100% | 6
|  | 3.1.6 | Barter POS | Development | Suki App | Barter POS | NONE | NONE |  |  | 4 | 2020-05-01 | 2020-05-08 | 8 | COMPLETE | 1 | 100% | 6
|  | 3.1.7 | Multiple Branch Capabilities | Development | Suki App | Multiple Branch Capabilities | NONE | NONE |  |  | 4 | 2020-05-01 | 2020-05-08 | 8 | COMPLETE | 1 | 100% | 6
|  | 3.1.8 | Customer Loyalty Points | Development | Suki App | Customer Loyalty Points | NONE | NONE |  |  | 4 | 2020-05-01 | 2020-05-08 | 8 | COMPLETE | 1 | 100% | 6
|  | 4 | System Integration Testing | System Integration Testing | NONE | NONE | NONE | NONE | BP |  | 2 | 2020-05-01 | 2020-05-11 | 7 | COMPLETE | 1 | 100% | 7
|  | 4.1 | Test Scripts Creation | System Integration Testing | Test Scripts Creation | NONE | NONE | NONE |  |  | 3 | 2020-05-04 | 2020-05-09 | 6 | COMPLETE | 1 | 100% | 5
|  | 4.1.1 | System Integration Testing | System Integration Testing | Test Scripts Creation | System Integration Testing | NONE | NONE |  |  | 4 | 2020-05-10 | 2020-05-10 | 1 |  |  | 100% | 0
|  | 4.1.2 | Bugs Fixing | System Integration Testing | Test Scripts Creation | Bugs Fixing | NONE | NONE |  |  | 4 | 2020-05-10 | 2020-05-10 | 1 |  |  | 100% | 0
|  | 4.1.3 | Re-testing | System Integration Testing | Test Scripts Creation | Re-testing | NONE | NONE |  |  | 4 | 2020-05-10 | 2020-05-10 | 1 |  |  | 100% | 0
|  | 4.1.4 | Sign-off | System Integration Testing | Test Scripts Creation | Sign-off | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-11 | 1 |  |  | 100% | 1
|  | 5 | Training | Training | NONE | NONE | NONE | NONE | JM/EA/ AC/BP |  | 2 | 2020-05-07 | 2020-05-12 | 4 | COMPLETE | 1 | 100% | 4
|  | 5.1 | Suki App | Training | Suki App | NONE | NONE | NONE | Acodilla |  | 3 | 2020-05-07 | 2020-05-07 | 1 | COMPLETE | 1 | 100% | 1
|  | 5.1.1 | Suki Hub | Training | Suki App | Suki Hub | NONE | NONE | Acodilla |  | 4 | 2020-05-11 | 2020-05-11 | 1 | COMPLETE | 1 | 100% | 1
|  | 5.1.2 | Picker-Checker-Driver | Training | Suki App | Picker-Checker-Driver | NONE | NONE | Acodilla |  | 4 | 2020-05-12 | 2020-05-12 | 1 | COMPLETE | 1 | 100% | 1
|  | 6 | PRG Business Process Creation - BRD | PRG Business Process Creation - BRD | NONE | NONE | NONE | NONE | GS/JV |  | 2 | 2020-04-17 | 2020-05-13 | 19 |  |  | 100% | 19
|  | 6.1 | BRD Creation | PRG Business Process Creation - BRD | BRD Creation | NONE | NONE | NONE |  |  | 3 | 2020-04-17 | 2020-04-28 | 12 |  |  | 100% | 8
|  | 6.1.1 | Suki App | PRG Business Process Creation - BRD | BRD Creation | Suki App | NONE | NONE |  |  | 4 | 2020-04-17 | 2020-04-28 | 12 |  |  | 100% | 8
|  | 6.1.2 | Suki Hub | PRG Business Process Creation - BRD | BRD Creation | Suki Hub | NONE | NONE |  |  | 4 | 2020-04-17 | 2020-04-28 | 12 |  |  | 100% | 8
|  | 6.1.3 | Picker-Checker | PRG Business Process Creation - BRD | BRD Creation | Picker-Checker | NONE | NONE |  |  | 4 | 2020-04-17 | 2020-04-28 | 12 |  |  | 100% | 8
|  | 6.1.4 | Daily Inventory Uploading and Branch synching | PRG Business Process Creation - BRD | BRD Creation | Daily Inventory Uploading and Branch synching | NONE | NONE |  |  | 4 | 2020-04-17 | 2020-04-28 | 12 |  |  | 100% | 8
|  | 6.1.5 | Suki Agent | PRG Business Process Creation - BRD | BRD Creation | Suki Agent | NONE | NONE |  |  | 4 | 2020-04-17 | 2020-04-28 | 12 |  |  | 100% | 8
|  | 6.1.6 | Customer Loyalty Points | PRG Business Process Creation - BRD | BRD Creation | Customer Loyalty Points | NONE | NONE |  |  | 4 | 2020-04-17 | 2020-04-28 | 12 |  |  | 100% | 8
|  | 6.1.7 | Data Management | PRG Business Process Creation - BRD | BRD Creation | Data Management | NONE | NONE |  |  | 4 | 2020-04-17 | 2020-04-28 | 12 |  |  | 100% | 8
|  | 6.1.8 | Payment Collections | PRG Business Process Creation - BRD | BRD Creation | Payment Collections | NONE | NONE |  |  | 4 | 2020-04-17 | 2020-04-28 | 12 |  |  | 100% | 8
|  | 6.1.9 | Exceptions and Limitations | PRG Business Process Creation - BRD | BRD Creation | Exceptions and Limitations | NONE | NONE |  |  | 4 | 2020-04-17 | 2020-04-28 | 12 |  |  | 100% | 8
|  | 6.1.10 | Support Org Chart | PRG Business Process Creation - BRD | BRD Creation | Support Org Chart | NONE | NONE |  |  | 4 | 2020-04-17 | 2020-04-28 | 12 |  |  | 100% | 8
|  | 6.1.11 | Customer Awareness | PRG Business Process Creation - BRD | BRD Creation | Customer Awareness | NONE | NONE |  |  | 4 | 2020-04-17 | 2020-04-28 | 12 |  |  | 100% | 8
|  | 6.1.12 | Guidelines and policies | PRG Business Process Creation - BRD | BRD Creation | Guidelines and policies | NONE | NONE |  |  | 4 | 2020-04-17 | 2020-04-28 | 12 |  |  | 100% | 8
|  | 6.2 | BRD Submission | PRG Business Process Creation - BRD | BRD Submission | NONE | NONE | NONE |  |  | 3 | 2020-04-29 | 2020-04-29 | 1 |  |  | 100% | 1
|  | 6.3 | BRD Processing | PRG Business Process Creation - BRD | BRD Processing | NONE | NONE | NONE |  |  | 3 | 2020-04-30 | 2020-05-13 | 14 |  |  | 100% | 10
|  | 7 | Configuration and Migration | Configuration and Migration | NONE | NONE | NONE | NONE | BP |  | 2 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 7.1 | Configure Business Settings | Configuration and Migration | Configure Business Settings | NONE | NONE | NONE |  |  | 3 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 7.1.1 | Company Configuration | Configuration and Migration | Configure Business Settings | Company Configuration | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 7.1.2 | Service Level Agreement | Configuration and Migration | Configure Business Settings | Service Level Agreement | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 7.1.3 | Shipping Rates | Configuration and Migration | Configure Business Settings | Shipping Rates | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 7.1.4 | Advanced Configuration | Configuration and Migration | Configure Business Settings | Advanced Configuration | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 7.1.5 | Configure User Accesss for Suki Hub | Configuration and Migration | Configure Business Settings | Configure User Accesss for Suki Hub | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 7.1.6 | Provide complete list of Users | Configuration and Migration | Configure Business Settings | Provide complete list of Users | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 7.1.7 | Configure Users | Configuration and Migration | Configure Business Settings | Configure Users | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 8 | Data Migration | Data Migration | NONE | NONE | NONE | NONE | KT |  | 2 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 8.1 | Master Products | Data Migration | Master Products | NONE | NONE | NONE |  |  | 3 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 8.1.1 | Popular Products | Data Migration | Master Products | Popular Products | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 8.1.2 | Membership Data | Data Migration | Master Products | Membership Data | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 8.1.3 | Inventory | Data Migration | Master Products | Inventory | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 |  |  | 100% | 5
|  | 8.1.4 | Images | Data Migration | Master Products | Images | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 87% | 5
|  | 9 | Infrastructure | Infrastructure | NONE | NONE | NONE | NONE | AC |  | 2 | 2020-04-30 | 2020-05-12 | 9 | COMPLETE | 1 | 100% | 9
|  | 9.1 | Stable Internet Connection | Infrastructure | Stable Internet Connection | NONE | NONE | NONE |  |  | 3 | 2020-04-30 | 2020-04-30 | 1 | COMPLETE | 1 | 100% | 1
|  | 9.1.1 | Wifi acess for entire Store | Infrastructure | Stable Internet Connection | Wifi acess for entire Store | NONE | NONE |  |  | 4 | 2020-04-30 | 2020-04-30 | 1 | COMPLETE | 1 | 100% | 1
|  | 9.1.2 | Suki Hardware | Infrastructure | Stable Internet Connection | Suki Hardware | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-12 | 2 | COMPLETE | 1 | 100% | 2
|  | 9.1.3 | PDTs | Infrastructure | Stable Internet Connection | PDTs | NONE | NONE |  |  | 4 | 2020-05-12 | 2020-05-12 | 1 | COMPLETE | 1 | 100% | 1
|  | 9.1.4 | LAN Receipt Printer for Picker | Infrastructure | Stable Internet Connection | LAN Receipt Printer for Picker | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-12 | 2 | COMPLETE | 1 | 100% | 2
|  | 9.1.5 | Dedicated Barter POS | Infrastructure | Stable Internet Connection | Dedicated Barter POS | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-12 | 2 | COMPLETE | 1 | 100% | 2
|  | 9.1.6 | Barter POS Hardware | Infrastructure | Stable Internet Connection | Barter POS Hardware | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-12 | 2 | COMPLETE | 1 | 100% | 2
|  | 10 | Pre Live Checklist/Preparation | Pre Live Checklist/Preparation | NONE | NONE | NONE | NONE | AC |  | 2 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 10.1 | Install and configure all Hardwares | Pre Live Checklist/Preparation | Install and configure all Hardwares | NONE | NONE | NONE |  |  | 3 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 10.1.1 | PDTs | Pre Live Checklist/Preparation | Install and configure all Hardwares | PDTs | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 10.1.2 | LAN Receipt Printer for Picker | Pre Live Checklist/Preparation | Install and configure all Hardwares | LAN Receipt Printer for Picker | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 |  |  | 100% | 5
|  | 10.1.3 | Dedicated Barter POS | Pre Live Checklist/Preparation | Install and configure all Hardwares | Dedicated Barter POS | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 10.1.4 | Double check all Hardwares if working | Pre Live Checklist/Preparation | Install and configure all Hardwares | Double check all Hardwares if working | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 10.1.5 | Check if all Hardwares if working | Pre Live Checklist/Preparation | Install and configure all Hardwares | Check if all Hardwares if working | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 10.1.6 | PDTs and Printer | Pre Live Checklist/Preparation | Install and configure all Hardwares | PDTs and Printer | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 10.1.7 | POS | Pre Live Checklist/Preparation | Install and configure all Hardwares | POS | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 10.1.8 | Wifi speed and availability in entire Stores | Pre Live Checklist/Preparation | Install and configure all Hardwares | Wifi speed and availability in entire Stores | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 10.1.9 | Double check and stress test Middleware | Pre Live Checklist/Preparation | Install and configure all Hardwares | Double check and stress test Middleware | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 10.1.10 | Checklist | Pre Live Checklist/Preparation | Install and configure all Hardwares | Checklist | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 10.1.11 | Do we have Pickers? | Pre Live Checklist/Preparation | Install and configure all Hardwares | Do we have Pickers? | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 |  |  | 100% | 5
|  | 10.1.12 | Do we have central contact or lines? | Pre Live Checklist/Preparation | Install and configure all Hardwares | Do we have central contact or lines? | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 |  |  | 100% | 5
|  | 10.1.13 | Do we have Checker? | Pre Live Checklist/Preparation | Install and configure all Hardwares | Do we have Checker? | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 |  |  | 100% | 5
|  | 10.1.14 | Do we have Delivery vehicle and driver? | Pre Live Checklist/Preparation | Install and configure all Hardwares | Do we have Delivery vehicle and driver? | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 |  |  | 100% | 5
|  | 10.1.15 | Do we have dedicated lanes/section for Pickup? | Pre Live Checklist/Preparation | Install and configure all Hardwares | Do we have dedicated lanes/section for Pickup? | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 |  |  | 100% | 5
|  | 10.1.16 | Do we have dedicated resource for Money remittances? | Pre Live Checklist/Preparation | Install and configure all Hardwares | Do we have dedicated resource for Money remittances? | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 |  |  | 100% | 5
|  | 11 | Dry Run | Dry Run | NONE | NONE | NONE | NONE | JM/EA/ AC |  | 2 | 2020-05-11 | 2020-05-26 | 12 | COMPLETE | 1 | 100% | 12
|  | 11.1 | Setup of Hardware and Connectivity | Dry Run | Setup of Hardware and Connectivity | NONE | NONE | NONE |  |  | 3 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 11.1.1 | Setup of Barter Suki Integration | Dry Run | Setup of Hardware and Connectivity | Setup of Barter Suki Integration | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 11.1.2 | Setup Picker-Checker-Driver Apps | Dry Run | Setup of Hardware and Connectivity | Setup Picker-Checker-Driver Apps | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 11.1.3 | Onboard assigned resources for Picker-Checker-Driver | Dry Run | Setup of Hardware and Connectivity | Onboard assigned resources for Picker-Checker-Driver | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 11.1.4 | Goods Fill Rate | Dry Run | Setup of Hardware and Connectivity | Goods Fill Rate | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 11.1.5 | Data re-synching | Dry Run | Setup of Hardware and Connectivity | Data re-synching | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-15 | 5 | COMPLETE | 1 | 100% | 5
|  | 11.1.6 | Trial Run (Targeted Customers) | Dry Run | Setup of Hardware and Connectivity | Trial Run (Targeted Customers) | NONE | NONE |  |  | 4 | 2020-05-25 | 2020-05-26 | 2 | COMPLETE | 1 | 100% | 2
|  | 11.1.7 | Hypercare | Dry Run | Setup of Hardware and Connectivity | Hypercare | NONE | NONE |  |  | 4 | 2020-05-11 | 2020-05-26 | 16 | COMPLETE | 1 | 100% | 12
|  | 12 | Marketing Advertisements/Promotions | Marketing Advertisements/Promotions | NONE | NONE | NONE | NONE | DT |  | 2 | 2020-05-28 | 2020-05-29 | 2 | COMPLETE | 1 | 100% | 2
|  | 12.1 | Flyers | Marketing Advertisements/Promotions | Flyers | NONE | NONE | NONE |  |  | 3 | 2020-05-28 | 2020-05-29 | 2 | COMPLETE | 1 | 100% | 2
|  | 12.1.1 | Social Sites (Organique) | Marketing Advertisements/Promotions | Flyers | Social Sites (Organique) | NONE | NONE |  |  | 4 | 2020-05-28 | 2020-05-29 | 2 | COMPLETE | 1 | 100% | 2
|  | 12.1.2 | Freebies/GCs | Marketing Advertisements/Promotions | Flyers | Freebies/GCs | NONE | NONE |  |  | 4 | 2020-05-28 | 2020-05-29 | 2 | COMPLETE | 1 | 100% | 2
|  | 13 | Go Live | Go Live | NONE | NONE | NONE | NONE | JM/EA |  | 2 | 2020-05-15 | 2020-12-07 | 147 |  |  | 100% | 147
|  |  |  | 0 | NONE | NONE | NONE | NONE |  |  | 2
48%
COMPLETION

## Risk and Issue Management
Risks | Classifications | Mitigation Plan | Subject | Issues | IMPACT | Action Plans | Owner | Date Assigned | Deadline | Date Closed | Status | Remarks
| HIGH |  |  |  | LOW | [5 empty] | Pending
| HIGH |  |  |  | MEDIUM | [5 empty] | Resolution In Progress
[5 empty] | HIGH | [5 empty] | Closed

## Project Team
Name | Position | Department | Section | Project Role | Business Email Address | Mobile Number | Days Available | Comment

## Communication Plan
Agenda | Required Communication | Start | Finish | Duration | Status | Intitiated By | Required Attendance | Purpose

## Stakeholder Management
Name | Position | Project Role | Business Email Address | Preferred Communication Type | Project Expectations | Infuence | Comments